## Project
Total Project Tracking
Total Iteration should be: [TBD] |  |  |  |  | Number of project members: [TBD]
Function Name | Feature | Screen Name | Complexity | Planned Code Iteration | Student No | In-charge Full Name | Actual Code Iteration | SRS Status | Design Status | Coding Status | Testing Status | % Completed | Completed in Iteration
User Login | Authentication | Login Page | Medium |  |  |  |  | Done | Done | Done | Done
User Register | Authentication | Register Page | Medium |  |  |  |  | Done | Done | Done | Done
Reset Password | Authentication | Forgot/Reset Password Page | Medium |  |  |  |  | Done | Done | Done | Doing
User Profile | Account Management | Profile Page | Simple |  |  |  |  | Done | Done | Done | To Do
Change Password | Account Management | Settings - Change Password | Simple |  |  |  |  | Done | Done | Done | To Do
Learn Grammar | Learning Content | Grammar Page | Medium |  |  |  |  | Done | Done | Done | Doing
Learn Kanji | Learning Content | Kanji List / Kanji Practice Page | Medium |  |  |  |  | Done | Done | Done | Doing
Learn Kana | Learning Content | Kana List Page | Simple |  |  |  |  | Done | Done | Done | Doing
Vocabulary | Learning Content | Vocabulary Home / Lesson List Page | Medium |  |  |  |  | Done | Done | Done | Doing
Take JLPT Mock Test | Testing & Assessment | Mock Test List / Attempt / Results Page | Complex |  |  |  |  | Done | Done | Done | Done
Practice & Quiz | Testing & Assessment | Quiz Page | Medium |  |  |  |  | Done | Done | Done | Done
Flashcard Learning | Flashcard SRS | Flashcard Session / Notebook Page | Complex |  |  |  |  | Done | Done | Done | Done
Speaking Practice & AI Grading | AI Practice | Speaking Practice Page | Complex |  |  |  |  | Done | Done | Doing | To Do
Reading Practice | Learning Content | Reading Page | Medium |  |  |  |  | Done | Done | Done | To Do
Listening Practice | Learning Content | Lesson Detail / Mock Test (embedded, no standalone screen) | Medium |  |  |  |  | Done | Done | Doing | To Do
Dictionary & Search | Dictionary & Search | Dictionary Page | Medium |  |  |  |  | Done | Done | Done | To Do
Bookmark Learning | Personalization | Notebook Page | Simple |  |  |  |  | Done | Done | To Do | To Do
Logout | Authentication | Global Nav action (no dedicated screen) | Simple |  |  |  |  | Done | Done | Done | Doing
Learning Progress & Stats | Progress Tracking | Progress Page | Medium |  |  |  |  | Done | Done | Done | To Do
AI Handwriting Practice | AI Practice | Kanji Practice Page (stroke-order canvas only, no OCR yet) | Complex |  |  |  |  | Done | Done | To Do | To Do
View Student Progress | Student Management | Staff Students Page | Medium |  |  |  |  | Done | Done | Done | To Do
Manage Student Accounts | Student Management | Staff Students Page | Medium |  |  |  |  | Done | Done | Done | To Do
Suspend or Activate Account | Student Management | Staff Students Page | Simple |  |  |  |  | Done | Done | Done | To Do
Manage Question Bank | Content Management | Staff Questions Page | Complex |  |  |  |  | Done | Done | Done | To Do
Manage Grammar Content | Content Management | Staff Content Page - Grammar tab | Medium |  |  |  |  | Done | Done | Done | To Do
Manage Quiz | Content Management | Staff Content Page - Quiz tab | Medium |  |  |  |  | Done | Done | Done | Done
Manage Learning Content | Content Management | Staff Content Page - Lesson/Course tab | Complex |  |  |  |  | Done | Done | Done | Done
Manage JLPT Mock Exams | Content Management | Staff Content Page - Exam tab | Complex |  |  |  |  | Done | Done | Done | Done
Respond to Student Support | Support | Staff Tickets Page | Medium |  |  |  |  | Done | Done | Done | Done
Send Notifications | Notification | Manager/Staff Notifications | Medium |  |  |  |  | Done | Done | Done | Done
Grade Speaking Submission | Support | Staff Grading Page | Medium |  |  |  |  | Done | Done | Doing | To Do
View Quiz Results | Analytics & Reporting | Staff Assessments Page | Medium |  |  |  |  | Done | Done | Doing | To Do
Review Submitted Content | Content Review | Manager Review Queue Page | Complex |  |  |  |  | Done | Done | Done | Done
Manage Published Content Status | Content Review | Manager Content Pipeline Page | Complex |  |  |  |  | Done | Done | Done | Done
Login System (Admin Panel) | Authentication | Login Page (shared) | Medium |  |  |  |  | Done | Done | Done | Doing
View Dashboard | System Administration | Admin Dashboard Page | Medium |  |  |  |  | Done | Done | Done | To Do
User Management | System Administration | Admin Manage Users Page | Complex |  |  |  |  | Done | Done | Done | Done
Report Screen | Analytics & Reporting | Admin Reports Page | Medium |  |  |  |  | Done | Done | Done | To Do
Settings | System Administration | Admin Settings Page | Medium |  |  |  |  | Done | Done | Done | To Do
Notification Rules | Notification | Admin Settings Page - Notification tab | Medium |  |  |  |  | Done | Done | Done | Done

## Iter1
Iteration Tracking - Iteration 1
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
| Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
| Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter2
Iteration Tracking - Iteration 2
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
| Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
| Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter3
Iteration Tracking - Iteration 3
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
| Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
| Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document

## Iter4
Iteration Tracking - Iteration 4
Information in the columns A-F must be provided as the planned scope for the iteration
Columns B-D are copied from the sheet Product
Columns E-J are updated/filled by the end of the iteration
# | Screen / Function | Feature | Screen/Function Description | In Charge | Status | SRS | SDS | Notes
| Screen/Function Name1 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tuấn Hà | Done | II.3 | III.5
| Screen/Function Name2 | Feature Name1 | This is short descripiton for the screen/function (2-3 sentences) | Tử Vinh | To Do | II.1 | III.4
Note on G5: KienNT: The name of section in the SRS (software requirement specification) document
Note on H5: KienNT: The name of section in the SDS (software design specification) document